Work plan

Deadlines

2018-02-26 Choose a project proposal and send your choice via email to epsatisep@gmail.com

2018-03-05 Define the Tasks (what must be done - every member should preferably participate in every task), subtask allocation (who does what) and Gantt chart (when) of the project and insert them on the wiki (planning)

2018-03-12 Upload the “black box” System Diagrams & Structural Drafts to the wiki

2018-03-23 Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure

2018-04-04 Upload the List of Materials (what & quantity) to the wiki

2018-04-14 Upload the Interim Report and Presentation to the wiki. The report must contain the Introduction, including the tasks, team members allocation and Gantt chart, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography chapters

2018-04-19 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks

2018-04-23 Complete the List of Materials (local providers & price, including VAT and transportation) to the wiki

2018-05-02 Upload refined Interim Report (based on Teacher & Supervisor Feedbacks)

2018-06-04 Upload the results of the Functional Tests to the wiki

2018-06-15 Upload the Final Report

2018-06-18 Upload the Presentation, Video, Paper, Poster and Manual

2018-06-21 Final Presentation, Individual Discussion and Assessment

2018-06-28:

Update the wiki with all correction suggestions

Hand in to the EPS coordinator:

a CD with the corrected deliverables (source + PDF) together with all code and drawings produced

a printed copy of the corrected report and poster

2018-06-28:

Hand in the prototype and user manual to the client

Receive the EPS@ISEP certificate

Bring typical food from your country

Tasks

Task	Responsible	Involved
A	X and Y	X, Y, Z, W
B	Z	X, Y, Z, W
C	W, Y and Z	X, Y, Z, W
D	W	X, Y, Z
E	W, X, Y and Z	X, Y, Z, W
F	X	X, Y, Z, W
G	W and X	X, Y, Z, W

Gantt Chart

first_gantt_chart.docx

second_gantt_chart_16-03-2018.docx

third_gantt_chart_23-03-2018.docx

fourth_gantt_chart_30-03-2018.docx

fifth_gantt_chart_06-04-2018.docx

sixth_gantt_chart_13-04-2018.docx

seventh_gantt_chart_20-04-2018.docx

eighth_gantt_chart_27-04-2018.docx

ninth_gantt_chart_04-05-2018.docx

tenth_gantt_chart_11-05-2018.docx

eleventh_gantt_chart_18-05-2018.docx

twelfth_gantt_chart_25-05-2018.docx

thirteenth_gantt_chart_01-06-2018.docx

fourteenth_gantt_chart_08-06-2018.docx

fifteenth_gantt_chart_15-06-2018.docx

microsoft_project_gantt_unzipped.zip