# Work plan
## Deadlines
- 2018-02-26 Choose a project proposal and send your choice via email to epsatisep@gmail.com
- 2018-03-05 Define the Tasks (what must be done - every member should preferably participate in every task), subtask allocation (who does what) and Gantt chart (when) of the project and insert them on the wiki (planning)
- 2018-03-12 Upload the “black box” System Diagrams & Structural Drafts to the wiki
- 2018-03-23 Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure
- 2018-04-04 Upload the List of Materials (what & quantity) to the wiki
- 2018-04-14 Upload the Interim Report and Presentation to the wiki. The report must contain the Introduction, including the tasks, team members allocation and Gantt chart, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography chapters
- 2018-04-19 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks
- 2018-04-23 Complete the List of Materials (local providers & price, including VAT and transportation) to the wiki
- 2018-05-02 Upload refined Interim Report (based on Teacher & Supervisor Feedbacks)
- 2018-06-04 Upload the results of the Functional Tests to the wiki
- 2018-06-15 Upload the Final Report
- 2018-06-18 Upload the Presentation, Video, Paper, Poster and Manual
- 2018-06-21 Final Presentation, Individual Discussion and Assessment
- 2018-06-28:
  - Update the wiki with all correction suggestions
  - Hand in to the EPS coordinator:
    - a CD with the corrected deliverables (source + PDF) together with all code and drawings produced
    - a printed copy of the corrected report and poster
- 2018-06-28:
  - Hand in the prototype and user manual to the client
  - Receive the EPS@ISEP certificate
  - Bring typical food from your country
## Tasks
Task	Responsible	Involved
A	X and Y	X, Y, Z, W
B	Z	X, Y, Z, W
C	W, Y and Z	X, Y, Z, W
D	W	X, Y, Z
E	W, X, Y and Z	X, Y, Z, W
F	X	X, Y, Z, W
G	W and X	X, Y, Z, W

## Gantt Chart
first_gantt_chart.docx
second_gantt_chart_16-03-2018.docx
third_gantt_chart_23-03-2018.docx
fourth_gantt_chart_30-03-2018.docx
fifth_gantt_chart_06-04-2018.docx
sixth_gantt_chart_13-04-2018.docx
seventh_gantt_chart_20-04-2018.docx
eighth_gantt_chart_27-04-2018.docx
ninth_gantt_chart_04-05-2018.docx
tenth_gantt_chart_11-05-2018.docx
eleventh_gantt_chart_18-05-2018.docx
twelfth_gantt_chart_25-05-2018.docx
thirteenth_gantt_chart_01-06-2018.docx
fourteenth_gantt_chart_08-06-2018.docx
fifteenth_gantt_chart_15-06-2018.docx
microsoft_project_gantt_unzipped.zip